## Requirements
PDF Task | Phase | Requirement | Type | Status | What was built / notes | Your action
1.1 | Phase 1: Environment Setup | Install required libraries | Mandatory | Done | requirements.txt lists langchain, openai, streamlit, newsapi-python plus langchain-openai and python-dotenv.
1.2 | Phase 1: Environment Setup | Obtain API keys (OpenAI, NewsAPI) | Mandatory | Done | Keys load from .env; README links to both key pages. Keys are not hardcoded. | Add your own OpenAI and NewsAPI keys to .env.
2.1 / 2.2 | Phase 2: LangChain Configuration | Create langchain_config.py, initialise OpenAI and prompt | Mandatory | Done | Prompt follows the PDF, with more detailed instructions. Uses modern langchain-openai instead of the deprecated LLMChain import.
3.1 - 3.3 | Phase 3: Streamlit Interface | Create app.py, basic UI, run command | Mandatory | Done | Run with: streamlit run app.py
4.1 | Phase 4: Enhancing the Tool | NewsAPI integration (get_news_articles, summarize_articles, get_summary, 2-variable prompt) | Mandatory | Done | All three functions kept under the PDF names; articles now include source, date and title.
4.2 | Phase 4: Enhancing the Tool | Update Streamlit app to use enhanced config | Mandatory | Done | app.py calls research(), which combines get_summary and llm_chain in one step.
5.1 / 5.2 | Phase 5: Testing and Validation | Test basic functionality; validate summary accuracy | Mandatory | Partial | 19 mocked unit tests pass and the Streamlit flow (login, search, save, trends) was tested. smoke_test.py added for the real end-to-end check. No real OpenAI/NewsAPI call was made here (no OpenAI key, restricted network). | Run: python smoke_test.py "your query" with your keys and compare the summary against the printed source articles.
6.1 | Phase 6: Documentation | Comments, documentation and README | Mandatory | Done | Docstrings in the code; README covers setup, usage, testing and limitations.
6.2 | Phase 6: Documentation | requirements.txt, final structure, clean up unused code | Mandatory | Done | requirements.txt and structure finalised; leftover line removed from app.py.
7.1 | Optional Enhancements | Add user authentication | Optional | Done | Login screen (auth.py): username and password from .env, plain or SHA-256 hashed, constant-time comparison. | Set AUTH_USERNAME and AUTH_PASSWORD in .env.
7.2 | Optional Enhancements | Enhance UI/UX | Optional | Done | Sidebar settings, spinner, expandable source articles.
7.3 | Optional Enhancements | Extend functionality (save queries, export, historical analysis) | Optional | Done | Saved queries in SQLite (save, reopen, delete, export) and a Trends tab with sentiment over time, distribution and history table.
Legend: blue text in the Status column is editable (dropdown: Done / Partial / Not done). The Summary sheet updates automatically.

## Summary
News Research Tool: requirements status
Group | Done | Partial | Not done | Total
Mandatory | 8 | 1 | 0 | 9
Optional | 3 | 0 | 0 | 3
All requirements | 11 | 1 | 0 | 12
Completion (Done / Total) | 91.67%
Mandatory completion (Done / Total) | 88.89%
Note: 'Partial' items count as not yet complete. Source: status judgements from the previous answer in this conversation.